## Slide 1: VOCAB VTC
Jan. 13, 2010

## Slide 2: VTC Agenda
Terms of Reference – take a look
Planning: Use-Case and Vocabulary Database Workshop – Feb. –March 2011
Planning: Taxonomy Workshop – May 2011
In attendance
  Don Henshaw
  Corrina Gries
  Margaret O’Brien
  Duane Costa
  Jason Downing
  John Porter
  Mark Servilla

## Slide 3: Discussion
Pre- meeting
  Various ontologies at AGU were presented
    Described metadata structures
    They had then made it an ontology
    Our metadata models would be pretty applicable

## Slide 4: DB Workshop Objectives
Finalize VOCAB “Terms of Reference”
define use cases for the keyword database and its development
identify suitable existing database structures or software for managing the controlled vocabulary and adopt or modify them to meet the use cases, and
develop procedures for capturing and managing keyword taxonomys

## Slide 5: DB Workshop Discussion
What software should be considered as candidates for managing the controlled vocabulary?
  Protege
  http://www.willpowerinfo.co.uk/thessoft.htm
  http://www.asindexing.org/i4a/pages/index.cfm?pageid=3624
  http://sourceforge.net/projects/tematres/ (web-based, open source)
  Illiya Slezoskl for CUASHI – they have nice home grown system – relational database based – is it flexible enough for transfer to LTER? - Corrina
  GCMD folks, - SWEET – OWL now have multiple ontologies – John
  NBII - John
  HIVE – they might have suggestions - Dueane
  Lynn Yarmey – just finished some library work – Corrina knows
Workshop Logistics – When and Where
  At the LNO?
  At a field station?
  Possible dates? Feb 14-18, March 14-18????,
  Don- virtual, Duane – virtual, Margaret – interested, esp. in SB, Corrina- virtual,
  Mark- virtual, or in person, Jason – may be traveling
Items for workshop agenda?
  Would be good to come up with draft taxonomy
  Could shorten workshop by trying out software - 2 days

## Slide 6: Taxonomy Workshop
1-day workshop immediately prior to SC meeting (May 17, 2011)
Goal: complete several taxonomys
Straw man taxonomys produced prior to meeting
EB has promised to identify some domain scientists to work with us, BUT are there people you would like to suggest?
  Could work through list of attendees
  Check with IM on who is attending and their isuitablity

## Slide 7: Action Items
Shorten workshop to 2 days
  Could do on before or after NISAC at LNO – IMEXC is march 30
  Put out DOODLE poll for availablitity
ID Open source or low cost software
  J will assign people to packages for evaluation
  Margaret will find Protégé tutorial
  J will install opensource package
  Duane will send info on how to get to SKOS etc.
Terms of Reference
  Take a look
Contacting other groups to solicit input – as assigned
Set up doodle for VTC in first week of Feb.